Pioneer District Timeline

September 2006 – February 2007

| September |  |
| --- | --- |
| 19 - 20 | Local Evaluation Data Collection Tool Development Workshops |
| ?? | 2007 – 2012 IMPACT draft goes to AL State Board of Ed for approval |
| October |  |
| 16 | Pioneer Districts send drafts of tools and final versions of indicator rubrics to Sun |
| 16 | State Technology Survey open for online access (districts may start taking survey) |
| 27 | Pioneer Districts receive feedback on tools from Sun |
| November |  |
| 6 | Pioneer Districts start local data collection (using locally developed tools) |
| 17 | State Technology Survey closed for online access (districts must be done with survey-taking by this date) |
| December |  |
| 1 | Pioneer Districts’ mid-point check-in with Sun (to review local data collection progress and procedures for creating data summaries). Teleconf? F2F? |
| 15 | Pioneer Districts must complete local data collection (using locally developed tools) |
| 18 | Districts can access their state survey result reports from ALSDE |
| 18 | Districts start summary reports of local data |
| ?? | AL State Board of Ed approves final draft of 2007 – 2012 IMPACT |
| January |  |
| 12 | Districts send draft data summaries to Sun for review |
| 22 | (2 days during this week) Workshops on Evaluation Data Analysis, Use, and Reporting |
| February |  |
| 5 | (approximate) Release of final version of state survey – survey opens to statewide use |