Strategic Instructional Technology Plan

2013 - 2016

Sample District Public Schools

Table of Contents

1.  Introduction	4

Sample District’s Technology Planning Committee	5

District Mission	6

Sample District’s Vision for Instructional Technology	6

2. Technology Needs – Current Status	7

Summary Findings	7

Summary Recommendations	8

3.  2012 – 2015 Strategic Goals and Action Plans	10

Strategic Goals	10

Action Plans	11

Student and Teacher Skills	11

Policies	13

Infrastructure	17

4.  Evaluation and Assessment for Technology	19

Evaluation Design	19

Evaluation and Technology Plan Updates: 2013 – 2016	20

5.  Sample District’s Technology Organization	21

The Technology Committee	21

Technology Management and Staffing	21

Instructional Technology Integration Services	22

Infrastructure Services	22

Information Systems Services	23

Technical Support Services	24

6.  Technology Infrastructure	25

Current Configuration (Fall 2013)	25

Anticipated Expansion and Upgrades	25

7. Funding	26

Allocating funds within our Operating Budget	26

Grants and Private Funding	26

Establish community partnerships	26

Appendix I: Standards	27

NETS-S (Students)	27

NETS-T (Teachers)	29

NETS-A (Administrators)	30

Appendix II: Budget for Infrastructure	33

# 1.  Introduction

The following plan provides strategic direction and establishes specific action steps related to how the instructional technology will be implemented so as to benefit teaching and learning in the Sample District Public Schools over the next three calendar years. The Strategic Technology Plan is designed to provide a blueprint for district technology efforts.

The basic premise of this plan – as informed by research -- is that pedagogy and curriculum must drive instructional technology use.  Beyond this, the plan is also built upon the knowledge that Sample District students need teachers who understand how to teach in ways that foster the development of thinking skills as well as the acquisition of content knowledge. Technology has a role to play in supporting teachers in both of these tasks. The strategic directions of this plan aim to develop teacher skills, and to facilitate teacher use of technology to accomplish new tasks and to truly bring our school and the work that occurs within it into the 21st century.

We realize that we face considerable challenges in achieving our overall goal of utilizing technology tools to enrich and improve learning for all students.  As the Current Status chapter of this document shows, Sample District is warm, welcoming, and supportive community where teachers constantly strive to provide their students with an ideal learning environment.  It is clear that one aspect of this environment should be the application of instructional technology to support curriculum standards and other learning goals.  As with all work in our District, we find benefit in taking a measured, thoughtful, and strategic approach to technology integration.  In service of our District mission to address the needs of all children, we realize that a one-size-fits-all approach to technology integration will not work. Rather, we wish to provide teachers with the skills necessary to differentially apply technology as a tool for meeting each student’s unique needs and overall to develop the thinking and learning skills of all students.

Armed with the knowledge that we need to change how teachers think about learning and pedagogy and the tools used to accomplish both, a major thrust of this new Technology Plan is teacher professional development. Sample District will create professional development models and resources that can be implemented at the classroom level. New professional development efforts include work on mapping technology tools, and the NETS standards, onto core curriculum frameworks so that teachers can have specific, concrete, examples of how they can achieve the teaching of 21st century learning skills aligned with curriculum in their own classrooms.  This will be just one of a number of the major professional development efforts starting as soon as the Fall of 2013.

As noted above, a central principle that underlies this Technology Plan is that achievement of the ISTE NETS standards for students, teachers and administrators drives the work of this plan.  For the most part, NETS describe the desired outcomes for students/teachers/administrators as related to how technology is used to support 21st Century learning.  Meeting the NETS standards means creating learning environments that facilitate the development and practice of the types of thinking and learning that are necessary to success as a lifelong learner. This too is the over-arching goal of Sample District’s Strategic Technology Plan.

## Sample District’s Technology Planning Committee

## District Mission

The Sample District Public Schools is dedicated to creating a mutually caring, respectful and stimulating environment.  This will foster self-esteem and love of learning by empowering our children to excel academically, socially, creatively and physically.

The school district will develop evolving curricula and instructional methods to meet the needs of the children enabling them to experience success and to reach their full potential.

These goals are accomplished when the staff, parents, students and community work as partners to provide enriching educational experiences.  Our ultimate objective is to challenge all students to become self-motivated, lifelong learners and contributing members of society.

## Sample District’s Vision for Instructional Technology

We envision:

- Sample District’s students accessing, and purposefully utilizing, the technology tools and resources necessary to be actively engaged in individualized educational experiences that inspire a lifelong love of learning and the critical thinking skills necessary for success.

- A safe and comprehensive technology environment that addresses the needs of all users.

- Sample District’s teachers as skilled facilitators of an inquiry-based, student-centered learning environment, receiving embedded professional development that supports the utilization and active exploration of technology as a tool for transforming teaching and learning.

- Community recognition of the importance of ongoing investment in supporting, training, and equipping teachers and students with technology resources necessary to support student learning.

# 2. Technology Needs – Current Status

The Sample District Public Schools developed this Technology Plan to focus on the effective use of technology to support the implementation of the so-called “4Cs”:  communication, collaboration, critical thinking and creativity. These represent an explicit connection between technology use and a highly student-centered learning environment which emphasizes inquiry, information literacy, and is aligned with the Common Core Standards of learning.

Within this environment, teachers are intended to use technology to support inquiry and interdisciplinary, thematic, student-centered learning.  Technology is a tool that enables the types of learning environments desired for Sample District students.  Furthermore, a third indicator – one which is focused on the role of the district to support student and teacher outcomes – calls for a common culture that supports informal learning, conversations, and the development of teacher skills in technology and pedagogy. This is accomplished through teacher professional development that interweaves technology with broad initiatives such as the Common Core and inquiry-based learning, all supported by a commonly held vision for technology’s role in teaching and learning. Finally, the district’s infrastructure indicator calls for systems and resources to be available which support the district’s vision for teaching and learning.

These four indicators –Student Skills/Outcomes, Teacher Skills/Pedagogy, the Role of the District, and Infrastructure – formed the conceptual framework around which Sample District’s Instructional Technology Program was reviewed by Sun Associates in January, 2013.  Sun Associates is a professional educational program evaluation firm that specializes in Instructional Technology program review and strategic planning.  Sun Associates worked with Sample District administrators, community members, and staff to gather a wide range of survey, interview, focus group and classroom observation data from the Sample District School and its community.  Included in this collection was data from teachers, administrators, and parents. With data in-hand, the evaluators (Sun Associates) analyzed the district’s performance against its developed performance indicators. The findings and associated recommendations from that evaluative analysis (presented below) have subsequently formed the basis for Sample District’s Strategic Technology goals and action plans.

## Summary Findings

Overall, the evaluators find Sample District School to be a place where skilled, caring, and committed teachers and administrators work closely with relatively small groups of students.  The relatively small size of the district/school is largely a very positive thing.  There is a very keen sense of community in Sample District and it seems that nearly every parent and teacher is involved in some meaningful way with the operation of the district and the sustenance of its educational mission.  Further, the small size means that every teacher is in close contact with his/her peers, leading to a very supportive learning community.  Communication and collaboration among staff and administrators is simply easier in Sample District than would be the case in a larger district. Nevertheless, one downside of the small size is that the school cannot afford to have parents or teachers on “different pages” with regard to the vision about how the educational environment should be constructed.  In such a small environment, even small numbers of people who do not to participate in certain practices can create significantly inequitable impacts on students both within the school and in comparison to their peers in other school districts.

The evaluators find that while the district’s indicators for Student Skills/Outcomes related to technology are quite visionary and positive, in reality student technology use demonstrates a limited set of discrete skills related to the use of particular tools.  This occurs within a largely teacher-directed instructional environment that is not conducive to the development of student skills in the use of technology to support communication, collaboration, or critical thinking. In addition to the limited use of technology to support project based learning, the evaluators find that most student technology use is not currently student-centered, and teachers would generally benefit from professional development in integrating technology into their classrooms beyond expanded use of basic tools.

The evaluators root the student and teacher findings in actions that fall within the bounds of the Role of the District indicator.  Specifically, the evaluators find that Sample District teachers have very few professional development resources in technology and do not benefit from a commonly held vision for technology’s role in teaching and learning.  A strong consistent vision and the professional development necessary to support that vision, would go a long way in a small, close, district community such as Sample District School.  Furthermore, while the district is now subject to varied and often quite divergent parent opinions as to the value of technology, the district needs to establish a vision setting process that will align these divergent opinions and result in positive movement and support of a common vision. This work seems essential if Sample District is to move ahead with realizing the teaching and learning potential of instructional technology in the 21st century.

Finally, Infrastructure must support any vision, skills, and training that the district establishes.  While Sample District’s technology infrastructure is currently serviceable, it is in need of upgrade in the near future.  Teachers and students need to know that they will have the workstation power and network bandwidth necessary to fully participate in a 21st century learning environment.

## Summary Recommendations

The evaluators’ findings give rise to several basic recommendations for how Sample District could improve its Instructional Technology program.  These recommendations can, and should, all be part of the district’s strategic technology planning effort.

First and foremost, the district needs to establish a commonly held vision for technology’s role in supporting – as well as transforming - teaching and learning.  This vision should focus on technology’s role in helping Sample District’s students meet the challenges of life ahead in terms of becoming creative, collaborative, and critical life-long learners. Since this vision for student outcomes should not be specific to “technology”, it is necessary for the district to articulate the role of technology in meeting what should be in fact commonly held vision for learning.  The evaluators recommend that the Student Skills/Outcomes and Teacher Skills/Pedagogy indicators be used as the basis for a vision for instructional technology integration and therefore the cornerstone of the district’s new Instructional Technology Strategic Plan.

Next, Sample District needs to establish the professional development practices necessary to help teachers and students meet the district’s vision.  This professional development should generate exemplars, curriculum maps, and a scope and sequence of student technology skills that align with standards such as NETS, the Common Core, and the framework for 21st century learning.  In order to conduct such meaningful professional development, the district will need to evaluate the current role of its technology specialist to allow for the provision of job-embedded instructional support.

Finally, Sample District needs to improve its technology infrastructure over the near-term future.  As an immediate to-do, the district should upgrade its incoming network bandwidth to industry standard levels.  Subsequently, plans need to be made to upgrade teacher and student laptops, expand the network to accommodate a wider variety of devices (including tablets and student/teacher-owned devices), and to upgrade the wireless infrastructure to industry-standard commercial quality.

# 3.  2012 – 2015 Strategic Goals and Action Plans

## Strategic Goals

In overall support of Sample District’s vision for technology the district has established the following strategic instructional technology goals.

Student and Teacher Skills

- Instructional technology will be used as a catalyst and support for a student-centered, inquiry-based, pedagogy mapped to all core curriculum areas.

- Students will develop a uniform set of 21st century technology skills supportive of lifelong learning and success.

District Policies

- Encourage and support a culture for professional development that meets teachers’ needs in implementing instructional technology as a tool for teaching and learning.

- Ensure adequate staffing for instructional and technical support for students and staff.

- Evaluate, maintain, and update district policies that ensure the safe and ethical use of technology.

- Explore the policies and funding necessary to support a 1:1 student:device environment.

Infrastructure

- Evaluate, maintain, and update the district’s technology infrastructure to support the needs of all students and teachers.

- Maintain and evaluate district data and home/school communication systems.

## Action Plans

### Student and Teacher Skills

| GOAL: Instructional technology will be used as a catalyst and support for a student-centered, inquiry-based, pedagogy mapped to all core curriculum areas. |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013 – 2014 | Present technology goals and vision to SDPS faculty | Fall 2013 | Fall 2013 | None | Principal, School Technology Committee |
| 2014- 2015 | Align ISTE-NETS technology standards with the common core standards, district curriculum, and the Danielson framework. | Fall 2013 | Spring 2014 | $2500 Curriculum Writing | Principal (with assistance from Technology Specialist and Faculty) |
| 2013- 2014 | Develop SDPS curriculum guides that provide guidance to teachers as to how to meet NETS/Common Core skills through the academic curriculum. | Spring 2014 | on-going | Curriculum Writing -Professional Development $2500 | Principal Faculty |
| 2014 | Create bank of instructional activity ideas that correlate with the technology guides. | Fall 2013 | Ongoing | None | Technology Specialist (working with Faculty) |
| 2014 | Develop plans to utilize the Library Media Center as the hub for inquiry based/project based instruction. | Spring 2014 | Fall 2014 | $2000 | Principal, Technology Specialist, Library Media Specialist |
| 2014 | Develop a plan to prepare students and faculty for the use of technology as a tool for assessments that aligns with the NYS requirements for on-line assessments (e.g. PARCC). | Spring 2014 | Fall 2014 | $2000 | Technology Specialist Principal Library Media Specialist |
| GOAL: Students will develop a uniform set of 21st century technology skills supportive of lifelong learning and success. |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013 – 2015 | Integrate classroom learning with Library Media Center staff and resources through Professional Development. | September 2013 | Ongoing | $1000 | Library/Media Specialist |
| 2014- 2015 | Conduct teacher professional development regarding the student use of technology to support instruction in 21st century learning skills. | January 2014 | Ongoing | $5000 Imbedded Professional Development and BOCES Model Schools | Principal Library Media Specialist Technology Specialist Consultants |

### Policies

| GOAL: Encourage and support a culture for professional development that meets teachers’ needs in implementing instructional technology as a tool for teaching and learning |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013- 2014 | Define Teacher Skill Sets to Align w/Danielson Rubric/Framework to identify faculty needs and design appropriate professional development opportunities. | Fall 2013 | Fall 2013 | up to $5,000 for Professional Development | Superintendent, School Principal and Technology Specialist |
| 2013- 2014 | Insure protected time for Professional Learning - schedule time for collaboration and sharing of best practices. | 2013-2014 | 2013 - 2014 | none | School Principal |
| 2014- 2016 | Faculty Model effective use of instructional technology - Workshops, faculty meetings, etc. | 2014-2015 | 2015-2016 | none | All Faculty |
| 2014- 2016 | Earmark funding to engage facilitator(s) for a year long commitment for staff development and embedded training | 2014-2015 | 2015-2016 | $10,000/year for Consultant/ Facilitator | Superintendent |
| 2013- 2016 | Plan and implement monthly half days dedicated to staff training, imbedded professional development and coaching through flexible use of substitute staff. | 2013-2016 | ongoing | $5,000/year | School Principal |
| 2013- 2016 | Develop & promote opportunities for faculty sharing & collaboration (presentations at faculty meetings, after-school sessions, etc.) | 2013-2014 | ongoing | $5,000/year after school workshops | Superintendent School Principal |

| GOAL: Ensure adequate staffing for instructional and technical support for students and staff |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013- 2014 | Assess needs for instructional & technical support | Fall 2013 | Winter 2013 | none | Superintendent with Assistance of Technology Specialist |
| 2013- 2014 | Define and review job descriptions and staff roles for Instructional Technology Specialist (ITS), Testing Coordinator, District Data Coordinator, Chief Information Officer, Network Administrator, Library/Media Specialist, Technical Support (Contract Services), Technical/Clerical Support. | Fall 2013 | Winter 2013 | none | Superintendent |
| 2013- 2016 | Annually Evaluate Level of Technical Support Needed based on amount of growth in technology inventory and faculty/student use of technology. | Winter 2013 | Spring of each year | none | Superintendent with Assistance of Technology Specialist |
| 2013- 2014 | Evaluate Role and Responsibilities of Technology Specialist and Establish Priorities. | Fall 2013 | Spring 2014 | none | Superintendent |

| GOAL: Evaluate, maintain, and update district policies that ensure the safe and ethical use of technology |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013 | Approve Technology Plan | September 2013 | September 2013 | none | Superintendent |
| 2013- 2016 | Review and align all District policies with any new legislation and new use of technology in the District. | Fall 2013 | Spring 2016 | none | Superintendent |
| 2013 | Communicate vision and technology plan with the Sample District Staff and Community. | Fall 2013 | Fall 2013 | none | Superintendent |
| 2013 | Develop and communicate baseline criteria for use of personal learning devices. | Fall 2013 | Fall 2013 | none | School Principal & Superintendent |

| GOAL: Explore the policies and funding necessary to support a 1:1 student:device environment |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013- 2014 | Study options of BYOD vs. District Provided. | Winter 2013 | Early Spring 2014 | none | Technology Specialist |
| 2013- 2014 | Engage Administration and Faculty in Establishing Criteria for usage of 1:1 devices. | Fall 2013 | Spring 2014 | none | Superintendent |
| 2013- 2014 | Review Instructional Options for 1:1 Devices (in line with Sample District Guides for the use of Instructional Technology within the curriculum). | Winter 2013 | Spring 2014 | none | School Principal, Superintendent and Technology Specialist |
| 2013- 2016 | Annually Examine Funding Opportunities in order to prioritize initiatives. | Fall 2013 | Spring 2016 | none | Superintendent & School Business Administrator |
| 2014- 2015 | Purchase sufficient number of 1:1 devices for one grade level to pilot the implementation of 1:1 (A combination of BYOD and district-provided devices would allow additional grade level participation in the pilot.) | Winter 2014 | Summer 2015 | $15,000 Cost of Equipment | Technology Specialist |

### Infrastructure

| GOAL: Evaluate, maintain, and update the district’s technology infrastructure to support the needs of all students and teachers |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013 | Purchase and configure two new servers with a storage unit and upgrade networking software to Windows. | Summer 2013 | Summer 2013 | $28,600 | EduTek |
| 2013 | Plan and begin deploying a centrally managed wireless system and upgrade of network switches | Summer 2013 | Fall 2013 | $15,000 | Technology Specialist/EduTek |
| 2014- 2016 | Continue implementation of centrally managed wireless system and upgrading switches | Summer 2014 | Fall 2016 | $15,000 year/average cost | Technology Specialist/EduTek |
| 2013 | Create a replacement cycle plan to support technology tools for staff and students. | Fall 2013 | Fall 2013 | No Cost | Administration Technology Specialist/EduTek |
| 2014 | Support plans to utilize the LMC as a technology hub of the school by fostering student/faculty involvement, reviewing existing programs and determining future technology needs. | Fall 2014 | ongoing | TBD | Technology Committee (working with Library Media Specialist) |

| GOAL: Maintain and evaluate district data and home/school communication systems |
| --- |
| Year | Action Item | Start Date | Completion Date | Anticipated Cost | Lead Person |
| 2013 | Regularly evaluate communication and data systems utilized by the District. | Fall 2013 | ongoing | None | Technology Specialist/ Technology Committee |
| 2013 | Investigate and identify additional features of the student information system, school website, e-mail, and instructional tools and use the appropriate features to optimize communication between home and school. | Fall 2013 | ongoing | None | Technology Specialist/ Technology Committee |
| 2013 | Continually investigate other options to identify web 2.0 tools for communication and collaboration. | Fall 2013 | ongoing | None | Technology Specialist/ Technology Committee |
| 2014 | Support the implementation of a new, digital Elementary Report Card. | Fall 2014 | Summer 2016 | TBD | Principal (with Technology Specialist and faculty) |
| 2014 | Implement Google Apps for Education Environment. | Fall 2014 | Spring 2015 | $3,000 | Technology Specialist |
| 2013 | Provide Professional Development for incorporating new technology tools for home/school communication. | Fall 2013 | ongoing | $3,000 | Administration |

# 4.  Evaluation and Assessment for Technology

## Evaluation Design

Sample District is committed to conducting a systemic, rigorous, and highly formative evaluation process that aims to measure the impact that this Strategic Technology Plan is having in schools and classrooms throughout Sample District. This evaluation goes well beyond accounting for technology infrastructure and reporting quantitative data on students, teachers, and administrators achieving basic technology literacy benchmarks.  In addition to such basic data, the district’s technology plan evaluation effort will report on the qualitative impact of technology on teaching and learning.  Through such data, and the formative reflection on progress that this will support, Sample District will be in a position to monitor the impact of its technology infrastructure, technology policy, and technology professional development initiatives.  This will allow for responsive and frequent fine-tuning of efforts; and ultimately a much greater degree of accountability for the use of resources to support instructional technology.

Through this evaluation plan, Sample District will apply a uniform data collection process, using a standardized set of evaluation tools that have been specifically mapped to the plan’s goals and objectives.  These tools include teacher, student, and parent online survey instruments, classroom observation protocol, and interview/focus group questions for teachers and administrators.  Sample District will initiate a data collection effort in the spring of each school year that collects data at the classroom level. Information collected in this manner will create a uniform dataset to be used to determine the district’s progress toward meeting the indicators in the technology plan.

## Evaluation and Technology Plan Updates: 2013 – 2016

The following table describes the main activities associated with technology plan evaluation and technology plan updating between Fall 2013 and Fall 2016.

| Date | Activity | Responsibility | Product/Outcome |
| --- | --- | --- | --- |
| 2013 | Fall (October/November) | Develop data collection instruments | Admin. Staff | Data collection instruments properly mapped to technology plan indicators and other Sample District initiatives as necessary |
| 2014 | Spring (February) | Data Review (2013 data) | Admin. Staff School Staff |  |
|  | Spring (March/April) | Data Collection – Surveys, Focus Groups, Observations | Admin. Staff |  |
|  | Late Spring (May/June | Data Analysis and Reporting | Admin. Staff School Staff | Data reports and data review meeting with District and School Staff |
|  | Fall | Technology Plan Update | Admin. Staff School Staff | Updated District Plan |
| 2015 | Spring (February) | Data Review (2014 data) | Admin. Staff School Staff | Updated technology-related goals/actions |
|  | Spring (March/April) | Data Collection – Surveys, Focus Groups, Observations | Admin Staff |  |
|  | Late Spring (May/June) | Data Analysis and Reporting | Admin Staff School Staff | Data reports and data review meeting with District and School Staff |
|  | Fall | Technology Plan Update | Admin Staff School Staff | Updated District Plan and Updated School Technology Plans |
| 2016 | Spring (February) | Data Review (2015 data) with schools | Admin Staff School Staff | Updated technology-related goals/actions |
|  | Spring (March/April) | Data Collection – Surveys, Focus Groups, Observations | Admin Staff |  |
| 2016 | Summer | Data Analysis and Reporting | Admin Staff School Staff | Data reports and data review meeting with district and school staff |
|  | Fall | Technology Plan Revision | Outside Facilitator or Admin Staff School Staff | Revised District Plan (2016 – 2019) |

# 5.  Sample District’s Technology Organization

The Sample District Public Schools recognizes its responsibility to further the District’s instructional goals through the integration of appropriate, high quality technology with the instructional programs and administrative functions.  Key to this effort is the establishment of a strong connection between technology management and delivery of curriculum and instruction.  The necessary support for the oversight and management of this initiative will create a strong connection between the technology program and curriculum and instruction.

## The Technology Committee

With the implementation of the 2013 – 2016 Strategic Technology Plan, the focus of the District Technology Committee will be aligned with the vision for Instructional Technology as presented in this plan document.  The Technology Committee is composed of District stakeholders such as teachers, administrators, School Board members, parents and other community members.  This Committee will meet regularly to oversee the broad implementation of the District’s Technology Plan, and will serve to meet the District’s policy and procedures for the proper acquisition of technology.  The Committee will provide guidance and input into how the District interprets the technology needs and how these needs are met through the various initiatives, purchases, and actions of the district staff working to support technology as a tool for teaching and learning.  The advantages of this committee approach are clear and have been proven over the years.  Stakeholder involvement and oversight are critical for gaining the buy-in necessary for technology to be implemented meaningfully throughout the District.  Most importantly, by engaging regularly with this plan, the Technology Committee will insure that the plan is more than a “document on the shelf” but instead provide a roadmap that is focused on the needs of all learners and continually assessed as to its ability to meet and support the curriculum requirements.  To foster the connection between the technology program and curriculum and instruction, the Technology Committee will schedule a minimum of one joint meeting per year with the District’s Education Committee.

## Technology Management and Staffing

The structure for roles and responsibilities related to technology management and staffing are described in the following brief position descriptions.

Superintendent of Schools

The Superintendent oversees all District Technology operations, while collaborating with all areas of the district to provide technology solutions for instruction and administration.  This position is also responsible for professional development offerings, the department budget, project and staff management, district technology policy, industry trends assessment, planning, resource allocation and efficiency improvements. The Superintendent ensures that federal, state and district policies, such as CIPA, eRate technology needs, NYS Department of Education technology requirements are supported and completed.

School Business Administrator

The SBA is responsible for vendor contract negotiations, oversees vendor coordination, Information Systems’ budget development and management, and is responsible for vendor relations, project management, communications, and collaboration with district, regional, and state constituents to ensure mandates and needs are met efficiently and effectively.

### Instructional Technology Integration Services

School Principals

The School Principals work with the Technology Specialist to research, plan, coordinate, and oversee the implementation of district instructional technology initiatives for the schools.  This includes staff professional development, community collaboration and communication, and ongoing staff and school support.  This position oversees the Technology Specialist.

Technology Specialist

The Technology Specialist works directly with the School Principals and teaching staff to integrate District instructional technology initiatives. This work includes the development of ongoing face-to-face and on-demand staff professional development, the setup and management of ongoing central instructional technology solutions, as well as the evaluation and required modification of these initiatives to meet District instructional technology goals and timelines. The Technology Specialist will utilize the ISTE NETS-C standards for instructional technology coaching.  During the 2013-2014 school year, the responsibilities of the Technology Specialist will be evaluated and closely monitored to allow for appropriate allocation of time for instructional coaching.

### Infrastructure Services

Contract Service Provider

The management of the entire district network will be handled by a contract service provider.  This includes all managed network routers; network drops; wireless network access points; access controls; network and web security; data/server backup services and disaster recovery; power backup systems for all core network devices and data centers. The contract service provider serves as the Lead Support for the Infrastructure Services Team (currently fulfilled by X).

This contract service provider manages, supports and monitors all infrastructure data center and central District systems, including servers, applications, and power management. In addition, this provider oversees core enterprise solutions, system policy management, and thin client operations and assists with tier one network support services.

### Information Systems Services

Technology Specialist - Information Systems and School District Webpage

The Technology Specialist is responsible for the student information data systems, including data management and all administrative functions, and interfaces to peripheral databases and outside entities.  This position is responsible for overseeing the Student Information Services’ software system and maintaining district-wide content management sites.  The Technology Specialist coordinates data solutions for a variety of district instructional and operational departments.  This person verifies access to the Student Information System and manages the transfer of student and teacher data to the NYS student / teacher data systems, prepares district student information reports and oversees new software module implementations.   The position with the assistance of the School Guidance Counselor also provides Tier one student information system direct support to office and classroom staff, sets-up and maintains teacher accounts for the district’s Student Information System and provides onsite training.  This position performs continual data analysis to address issues preemptively and reports issues requiring program adjustments.

This position manages and regularly updates the district's website and homepage, including providing teacher access to class pages and eChalk training and support.

School Guidance Counselor

The School Guidance Counselor assists with the provision of Tier one student information system support and is responsible for maintaining the master schedule and student schedules, assisting with transcripts, report cards, interim reporting, graduation requirements, and course requests.

Chairperson of the Committee on Special Education

With the support of the contract software provider, IEP Direct, the Chairperson of the Committee on Special Education oversees all central Special Services data system applications and changes regarding Special Education practice and procedures. The Chairperson of the Committee on Special Education works closely with the support staff of IEPDirect to implement quality checks for compliance and coordinates required student records transitions.

This position manages any Student Services Assistive technology needs district-wide. This includes IEP technology compliance, classroom solutions, specialty software, systems, etc. Works with IEP teams to develop appropriate and efficient technology solutions for students with assistive technology needs.

### Technical Support Services

Technology Specialist

This position provides support for day-to-day technology operations, and customer service for District classroom, and administrative technologies.  This includes the management of purchased services, and technical support resources as well as hardware procurement, end station security, software management and asset management.  The Technology Specialist is expected to fully utilize the services of the Contract Service Provider to assist with these responsibilities.

# 6.  Technology Infrastructure

## Current Configuration (Fall 2013)

In general, technology tools and devices are available in all classrooms.  Every classroom has Internet access and is outfitted with a SmartBoard and ceiling mounted projector.  Each classroom has two, three or four desktop computers and a teacher laptop.  The Library Media Center (LMC) houses a computer lab with 24 desktops and a color printer.  The Middle School utilizes a laptop cart outfitted with 24 laptops purchased in the summer of 2013.  Eight teachers are currently piloting the use of iPads for classroom instruction.

Wireless access has been managed through individual wireless access points strategically located throughout the school building.  Certain areas of the school do not have access to wireless capabilities.  During the summer of 2013, the District began a phased infrastructure upgrade completing the first phase of the gradual conversion to a centrally managed wireless access system, replacing the three existing network servers with three virtual servers, and converting from Novel to a Windows operating system.

## Anticipated Expansion and Upgrades

The Sample District Public Schools will continue the gradual migration to a centrally managed district level wireless system.

To meet the requirements for New York State Partnership for Assessment of Readiness for College and Careers (PARCC) on line testing, the District will upgrade its network bandwidth.  In addition, the District will conduct an evaluation of existing technology infrastructure -- hardware and equipment -- and compare this with state requirements for on-line testing. The results of this review of District infrastructure will provide the necessary information to properly prepare for state testing mandates.

The District will follow the replacement cycle plan to periodically upgrade technology tools including desktops, laptops, tablets, Smart boards and affiliated peripherals. Additionally the use of personal mobile devices will be evaluated annually to address the need for additional technology devices to support student learning.

# 7. Funding

This multi-year living plan will be implemented from July 2013 through June 2016.  It is Sample District’s intent to begin the implementation of the goals and actions of this Strategic Technology Plan as soon as possible, in service of the district’s mission and overall vision of the plan.  Given that several of the action items identified in the plan require funding, the implementation of these items will be contingent on available funds.  The district plans to utilize the following funding sources in order to support implementation of these action items:  Allocation of funds within the operating budget, grants and private funding, and establishment of community partnerships.  These funding strategies are discussed in more detail below

### Allocating funds within our Operating Budget

Each year funds will be requested through the annual budget process.  The amount requested will vary based on the aggressiveness determined to implement the action items in a timely manner.  The 2013-2014 School Budget includes $X for the purpose of replacing aging computers.  This amount is based on replacing aging administrative and instructional desktops and other technology equipment (e.g. SmartBoard projectors) that have far exceeded their warranty periods.

### Grants and Private Funding

Efforts to identify grants and private funding are in process, not only for technology but for other areas of need as well.   Any funds received for this purpose will allow the District to accelerate implementation based on priorities unless there is a specific funding requirement that establishes a use of the funds that is not consistent with the priorities established in this plan. The speed of implementation will be based on opportunities and specific funding request requirements.

### Establish community partnerships

The District's Technology Committee will research and reach out to other community resources and establish partnerships.  A focus will be on matching action items to community expertise and determine if the community has the resources to assist with the implementation of identified action items.

# Appendix I: Standards

## NETS-S (Students)

1.  Creativity and Innovation -- Students demonstrate creative thinking, construct knowledge, and develop innovative products and processes using technology. Students:

a.	apply existing knowledge to generate new ideas, products, or processes.

b.	create original works as a means of personal or group expression.

c.	use models and simulations to explore complex systems and issues.

d. 	identify trends and forecast possibilities.

2.  Communication and Collaboration -- Students use digital media and environments to communicate and work collaboratively, including at a distance, to support individual learning and contribute to the learning of others. Students:

a.	interact, collaborate, and publish with peers, experts, or others employing a variety of digital environments and media.

b.	communicate information and ideas effectively to multiple audiences using a variety of media and formats.

c.	develop cultural understanding and global awareness by engaging with learners of other cultures.

d. 	contribute to project teams to produce original works or solve problems.

3.  Research and Information Fluency -- Students apply digital tools to gather, evaluate, and use information. Students:

a.	plan strategies to guide inquiry.

b.	locate, organize, analyze, evaluate, synthesize, and ethically use information from a variety of sources and media.

c.	evaluate and select information sources and digital tools based on the appropriateness to specific tasks.

d. 	process data and report results.

4.  Critical Thinking, Problem Solving, and Decision Making -- Students use critical thinking skills to plan and conduct research, manage projects, solve problems, and make informed decisions using appropriate digital tools and resources. Students:

a.	identify and define authentic problems and significant questions for investigation.

b.	plan and manage activities to develop a solution or complete a project.

c.	collect and analyze data to identify solutions and/or make informed decisions.

d. 	use multiple processes and diverse perspectives to explore alternative solutions.

5.  Digital Citizenship -- Students understand human, cultural, and societal issues related to technology and practice legal and ethical behavior. Students:

a.	advocate and practice safe, legal, and responsible use of information and technology.

b.	exhibit a positive attitude toward using technology that supports collaboration, learning, and productivity.

c.	demonstrate personal responsibility for lifelong learning.

d.	exhibit leadership for digital citizenship.

6.  Technology Operations and Concepts -- Students demonstrate a sound understanding of technology concepts, systems, and operations. Students:

a.	understand and use technology systems.

b.	select and use applications effectively and productively.

c.	troubleshoot systems and applications.

d. 	transfer current knowledge to learning of new technologies.

## NETS-T (Teachers)

1.  Facilitate and Inspire Student Learning and Creativity -- Teachers use their knowledge of subject matter, teaching and learning, and technology to facilitate experiences that advance student learning, creativity, and innovation in both face-to-face and virtual environments. Teachers:

a.	promote, support, and model creative and innovative thinking and inventiveness

b.	engage students in exploring real-world issues and solving authentic problems using digital tools and resources

c.	promote student reflection using collaborative tools to reveal and clarify students’ conceptual understanding and thinking, planning, and creative processes

d.	model collaborative knowledge construction by engaging in learning with students, colleagues, and others in face-to-face and virtual environments

2. Design and Develop Digital-Age Learning Experiences and Assessments -- Teachers design, develop, and evaluate authentic learning experiences and assessments incorporating contemporary tools and resources to maximize content learning in context and to develop the knowledge, skills, and attitudes identified in the NETS•S. Teachers:

a.	design or adapt relevant learning experiences that incorporate digital tools and resources to promote student learning and creativity

b.	develop technology-enriched learning environments that enable all students to pursue their individual curiosities and become active participants in setting their own educational goals, managing their own learning, and assessing their own progress

c.	customize and personalize learning activities to address students’ diverse learning styles, working strategies, and abilities using digital tools and resources

d.	provide students with multiple and varied formative and summative assessments aligned with content and technology standards and use resulting data to inform learning and teaching

3. Model Digital-Age Work and Learning -- Teachers exhibit knowledge, skills, and work processes representative of an innovative professional in a global and digital society. Teachers:

a.	demonstrate fluency in technology systems and the transfer of current knowledge to new technologies and situations

b.	collaborate with students, peers, parents, and community members using digital tools and resources to support student success and innovation

c.	communicate relevant information and ideas effectively to students, parents, and peers using a variety of digital-age media and formats

d.	model and facilitate effective use of current and emerging digital tools to locate, analyze, evaluate, and use information resources to support research and learning

4. Promote and Model Digital Citizenship and Responsibility -- Teachers understand local and global societal issues and responsibilities in an evolving digital culture and exhibit legal and ethical behavior in their professional practices. Teachers:

a.	advocate, model, and teach safe, legal, and ethical use of digital information and technology, including respect for copyright, intellectual property, and the appropriate documentation of sources

b.	address the diverse needs of all learners by using learner-centered strategies and providing equitable access to appropriate digital tools and resources

c.	promote and model digital etiquette and responsible social interactions related to the use of technology and information d.	develop and model cultural understanding and global awareness by engaging with colleagues and students of other cultures using digital-age communication and collaboration tools

5. Engage in Professional Growth and Leadership -- Teachers continuously improve their professional practice, model lifelong learning, and exhibit leadership in their school and professional community by promoting and demonstrating the effective use of digital tools and resources. Teachers:

a.	participate in local and global learning communities to explore creative applications of technology to improve student learning

b.	exhibit leadership by demonstrating a vision of technology infusion, participating in shared decision making and community building, and developing the leadership and technology skills of others

c.	evaluate and reflect on current research and professional practice on a regular basis to make effective use of existing and emerging digital tools and resources in support of student learning

d.	contribute to the effectiveness, vitality, and self-renewal of the teaching profession and of their school and community

## NETS-A (Administrators)

1. Visionary Leadership. Educational Administrators inspire and lead development and implementation of a shared vision for comprehensive integration of technology to promote excellence and support transformation throughout the organization. Educational Administrators:

a. 	inspire and facilitate among all stakeholders a shared vision of purposeful change that maximizes use of digital-age resources to meet and exceed learning goals, support effective instructional practice, and maximize performance of district and school leaders

b.          engage in an ongoing process to develop, implement, and communicate technology-infused strategic plans aligned with a shared vision c. advocate on local, state, and national levels for policies, programs, and funding to support implementation of a technology-infused vision and strategic plan

2. Digital-Age Learning Culture. Educational Administrators create, promote, and sustain a dynamic, digital-age learning culture that provides a rigorous, relevant, and engaging education for all students. Educational Administrators:

a.          ensure instructional innovation focused on continuous improvement of digital-age learning

b. 	model and promote the frequent and effective use of technology for learning

c. 	provide learner-centered environments equipped with technology and learning resources to meet the individual, diverse needs of all learners

d. 	ensure effective practice in the study of technology and its infusion across the curriculum

e. 	promote and participate in local, national, and global learning communities that stimulate innovation, creativity, and digital-age collaboration

3. Excellence in Professional Practice. Educational Administrators promote an environment of professional learning and innovation that empowers educators to enhance student learning through the infusion of contemporary technologies and digital resources. Educational Administrators:

a. 	allocate time, resources, and access to ensure ongoing professional growth in technology fluency and integration

b. 	facilitate and participate in learning communities that stimulate, nurture, and support administrators, faculty, and staff in the study and use of technology

c. 	promote and model effective communication and collaboration among stakeholders using digital-age tools

d. 	stay abreast of educational research and emerging trends regarding effective use of technology and encourage evaluation of new technologies for their potential to improve student learning

4. Systemic Improvement. Educational Administrators provide digital-age leadership and management to continuously improve the organization through the effective use of information and technology resources. Educational Administrators:

a. 	lead purposeful change to maximize the achievement of learning goals through the appropriate use of technology and media-rich resources

b. 	collaborate to establish metrics, collect and analyze data, interpret results, and share findings to improve staff performance and student learning

c. 	recruit and retain highly competent personnel who use technology creatively and proficiently to advance academic and operational goals

d. 	establish and leverage strategic partnerships to support systemic improvement e. establish and maintain a robust infrastructure for technology including integrated, interoperable technology systems to support management, operations, teaching, and learning

5. Digital Citizenship. Educational Administrators model and facilitate understanding of social, ethical, and legal issues and responsibilities related to an evolving digital culture. Educational Administrators:

a. 	ensure equitable access to appropriate digital tools and resources to meet the needs of all learners

b. 	promote, model, and establish policies for safe, legal, and ethical use of digital information and technology

c. 	promote and model responsible social interactions related to the use of technology and information

d. 	model and facilitate the development of a shared cultural understanding and involvement in global issues through the use of contemporary communication and collaboration tools

# Appendix II: Budget for Infrastructure

Note: The following budget was prepared by X and covers only the expenses associated with Sample District’s technology infrastructure.  Other expenses – such as curriculum initiatives, training – are specified where appropriate in the Action Plans.

| Planning Term: | 2013-14 |  |  |  |
| --- | --- | --- | --- | --- |
| Infrastructure |  |  |  |  |
|  | Description | Note | Budget | Schedule |
| New Firewall | Required to connect directly to Internet Service Provider |  | $XX,XXX | Summer of 2013 |
| Network Switches | Begin upgrading closet switches |  | $XX,XXX |  |
| Meru Wireless Upgrades | Begin deploying a centrally managed wireless system |  | $ XX,XXX | Summer of 2013 |
|  |  |  | $ XX,XXX |  |
| Servers/Storage |  |  |  |  |
|  | Description | Note | Budget | Schedule |
| 2 Additional HP Servers | Servers would be configured as host servers to support virtual servers |  | $ XX,XXX | Summer of 2013 |
| New Storage Unit | Required to combine host servers and provide redundancy |  | $ XX,XXX | Summer of 2013 |
| Lightspeed Rocket | Appliance for content filtering. Required to connect directly to Internet service Provider |  | $ XX,XXX | Summer of 2013 |
|  |  |  | $ XX,XXX |  |

(continued)

| Workstations |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Description | Note | Budget | Schedule |
| Workstations |  |  |  |  |
| Laptops |  |  |  |  |
| Mobile Devices |  |  |  |  |
|  |  |  | $ XX,XXX |  |
| Software |  |  |  |  |
|  | Description | Note | Budget | Schedule |
| Protekt Offsite Backup | Offsite Backup for critical data (500gb) |  | $ XX,XXX | Summer of 2013 |
| Lightspeed NextGen Software | Content filter subscription |  | $ XX,XXX | Summer of 2013 |
| Mobile Device Management | Depends on the districts deployment of mobile devices (iPad, Google Chromebooks… etc.) |  | TBD | TBD |
| Microsoft School Agreement | Provides all of the necessary Microsoft licensing including, operating systems, client access licenses as well as server software. | Will facilitate migrating to Windows 7 | $ XX,XXX | Summer of 2013 |
|  |  |  | $ XX,XXX |  |

# Text boxes

Superintendent

Board of Education Member (and parent)

Elementary Teacher

School Business Administrator

Elementary Principal

Secondary Teacher

Board of Education Member (and parent)

Technology Specialist

Board of Education Member (and parent)