Timeline for Year 1 VT LEAD-IT Team Evaluations

Summer – Fall, 2007

| Task | Description | Suggested Date |
| --- | --- | --- |
| 1. Finish Indicators and Review with Sun Associates | Complete 1 performance indicator per technology plan goal, and send review with Jeanne and/or Jeff | a.s.a.p. (task was identified in May as being completed in time for July institute) |
| 2. Create Data Collection Question Mapping | Map data collection questions to each indicator. (worksheet) | a.s.a.p. (task was identified in May as being completed in time for July Institute |
| 3. Review Data Collection Instruments with Sun Associates | Send draft surveys, focus group protocol, etc. to Jeanne and Jeff for review and comment | August 31 or sooner |
| 4. Collect Data | Administer surveys, conduct focus groups, gather classroom-level observation data, conduct interviews | September – 10/15/07 |
| 5. Create Data Summaries and Review with Sun Associates | Summarize each type of data so that it may be analyzed and used for scoring. Send summaries to Sun Associates for review prior to October regional meetings | 10/15/07 |
| 6. Regional Data Review Meetings | Meet with Sun Associates at VT Fest to discuss data analysis and scoring process. Review again report format. | Mid October (exact dates tbd) |
| 7. Submit Draft Evaluation Report to Sun Associates | Draft evaluation report, send to Sun Associates for feedback, comment. | 12/1/07 |
| 8. Create Final Report | Finalize evaluation report and distribute it within the SU/district | 12/15/07 or thereafter |